## prelim timing
Ford GEN 1M refresh - Workshop for R&D Effort Definition
|  |  |  | A Samples |  |  |  | B Samples |  |  |  | C Samples
| 2022 | [45 empty] | 2023
| Jan | Feb | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | Aug |  |  |  | Sept |  |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan
Discipline | CW ---> |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Electrical
EE - TBD
EE - TBD
Mechanical
FSM
ASPICE
Security Release
Update SW Reqs-Kernel
Gerber files A Sample
PCB lead time
A Samples
B Samples
C Samples Homologation (FCC, Canada, EU)
Gerber files B Sample
Wise release
Sample build
A.2 sample available
Code integration Basic SW : Cendric (driver available)
EOL manual
EOL Kernel
EOL Kernel Beta
Toolbox development
Toolbox available A sample
EOL2PC
Parametric
Environmental LTT sequence
System requirements and test case update
EMC activities( SW, HW, CFT) for DV SW
Update SW Reqs Basic SW
DV SW development
EMC tester sequence
PCB lead time
Sample build
Gerber files C Sample
PCB lead time
Platform integration: CENDRIC TSR : PASE, LF Tool, ASDM, RKE (5000 hours)
Sample build
MLC70 Engineering release
Toolbox development
B sample available
PCB lead time (series supplier)
Sample build
B sample available (series PCB)
Parametric
Environmental LTT sequence
DV SW Beta Drop
C sample available
C Samples DV/PV
Delta System testing
Delta System testing
Delta System testing
RC2
RC3
Toolbox available B sample
HW engineering testing (EV)
FSM4 ?
C Samples Homologation (Taiwan, Korea)
Application Development and integration: CENDRIC NAFTA: ??
Driver development and Application Development and integration:TLE92108 (dependency with Basic SW)
Application Development and integration:PROFET
Code implementation Basic SW : TLE92108 (spi configuration)
Code implementation Basic SW : MCAL ( I/O updates)
Application Development and integration: Integration with EOL Kernel and cyber
LF tool for Cendric calibration and calibration work
A.1 sample available (cendric only)
RC1
Cendric onlty EOL kernel and toolbox
RC2
RC3
PTS
SEC4 ?

## team
Arvind Awasthi | Project Execution Specialist
Wilfredo Martinez | EE
Alex Zuniga | ECAD
Raffy Sison | SW
Nancy Escobedo | SW
Edgar Perez-Navarro | SW
Sathish Somasundaram | Sys
Keerthi Biradavada | Sys
Sudhir Khed | Sys
Eduardo Sanchez | Sys
Doug Hornok | LTT
Luis Castaneda | EMC
Gerardo Rosas4 | Cyber Security
Carlos Navaratte | PTS engineer
Gerardo Sanchez | PTS engineer
Max Gaitan | ME
Bryan Madonna | PES
Rodrigo Cano | QMP
Mark Kenney | Homologation
Dave Reimus | RF
Miguel Menoyo | PM
Miguel Zavala-Mendoza | TPL
Hector Dominguez - NPLM | NPLM
Conrad Naegelin | QTPL